## Weekly Allocation
Status | Resource | Client | Project | Skill | Billable | time axis 2013-01-06 to 2014-01-05
 | time axis 2013-01-06 to 2013-12-29
Booked | Yong Gu | Intridea | Dashboard | Rails | TRUE |  | 2013-03-31: 40; 2013-04-07: 40; 2013-04-14: 40; 2013-04-21: 40; 2013-04-28: 40; 2013-05-05: 40; 2013-05-12: 40; 2013-05-19: 40; 2013-05-26: 40; 2013-06-02: 40; 2013-06-09: 10; 2013-06-16: 20; 2013-06-23: 30; 2013-06-30: 40
Booked | Jeff Baier | Intridea | Education | Rails | TRUE |  | 2013-04-21: 40; 2013-04-28: 40; 2013-05-05: 40; 2013-05-12: 40; 2013-05-19: 40; 2013-05-26: 40; 2013-06-02: 40; 2013-06-09: 40; 2013-06-16: 30; 2013-06-23: 20; 2013-06-30: 10

## Archived
Status | Resource | Client | Project | Skill | Billable | time axis 2012-01-08 to 2012-12-30
Billable | time axis 2012-01-08 to 2012-12-23
Booked | Anthony Nystrom | FBS | FlexMLS Contact Manager | PM | TRUE | 0
Booked | Brandon Hunter | FBS | FlexMLS Contact Manager | UX | TRUE | 0
Booked | Chris Tate | FBS | FlexMLS Contact Manager | UX | TRUE | 0
Booked | Jurgen Altziebler | FBS | FlexMLS Contact Manager | PM | TRUE | 0
Booked | Linus Liu | FBS | FlexMLS Contact Manager | QA | TRUE | 0
Booked | Peter Gumeson | FBS | FlexMLS Contact Manager | Rails | TRUE | 0
Booked | Serign Jobe | FBS | FlexMLS Contact Manager | Rails | TRUE | 32
Booked | Tom Zeng | FBS | FlexMLS Contact Manager | Rails | TRUE | 32
Booked | Anthony Nystrom | FBS | SOW2 - Home Page Development | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Booked | Brandon Hunter | FBS | SOW2 - Home Page Development | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Booked | Chris Tate | FBS | SOW2 - Home Page Development | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Booked | Jurgen Altziebler | FBS | SOW2 - Home Page Development | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Booked | Linus Liu | FBS | SOW2 - Home Page Development | QA | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 6; 2012-03-11: 6; 2012-03-18: 0
Booked | Michael Tierney | FBS | SOW2 - Home Page Development | HTML/JS | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 15; 2012-03-11: 15; 2012-03-18: 0
Booked | Roger Frost | FBS | SOW2 - Home Page Development | Rails | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Booked | Serign Jobe | FBS | SOW2 - Home Page Development | Rails | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 20; 2012-03-11: 20; 2012-03-18: 0
Booked | Tom Zeng | FBS | SOW2 - Home Page Development | Rails | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0
Pipeline | Anthony Nystrom | Chronicle | SOW3 - Trajan MVP | PM | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0
Pipeline | Jurgen Altziebler | Chronicle | SOW3 - Trajan MVP | PM | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0
Pipeline | Insiya Hussain | Chronicle | SOW3 - Trajan MVP | PM | FALSE |  | 2012-02-12: 24; 2012-02-19: 32; 2012-02-26: 32; 2012-03-04: 20; 2012-03-11: 20; 2012-03-18: 20; 2012-03-25: 20; 2012-04-01: 20; 2012-04-08: 20; 2012-04-15: 20; 2012-04-22: 20; 2012-04-29: 20; 2012-05-06: 20; 2012-05-13: 20; 2012-05-20: 20; 2012-05-27: 20; 2012-06-03: 20; 2012-06-10: 20; 2012-06-17: 20
Pipeline | Chris Tate | Chronicle | SOW3 - Trajan MVP | UX | FALSE |  | 2012-02-12: 20; 2012-02-19: 20; 2012-02-26: 20; 2012-03-04: 20; 2012-03-11: 20; 2012-03-18: 20; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0
Pipeline | Ben Markowitz | Chronicle | SOW3 - Trajan MVP | UX | FALSE |  | 2012-02-12: 20; 2012-02-19: 40; 2012-02-26: 40; 2012-03-04: 40; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0
Pipeline | TBD HTML/JS | Chronicle | SOW3 - Trajan MVP | HTML/JS | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 20; 2012-03-04: 40; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 40; 2012-04-22: 40; 2012-04-29: 40; 2012-05-06: 40; 2012-05-13: 40; 2012-05-20: 40; 2012-05-27: 40; 2012-06-03: 20; 2012-06-10: 20; 2012-06-17: 20
Pipeline | TBD HTML/JS | Chronicle | SOW3 - Trajan MVP | HTML/JS | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 20; 2012-04-29: 20; 2012-05-06: 20; 2012-05-13: 20; 2012-05-20: 20; 2012-05-27: 20; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0
Pipeline | TBD Rails | Chronicle | SOW3 - Trajan MVP | Rails | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 40; 2012-04-22: 40; 2012-04-29: 40; 2012-05-06: 40; 2012-05-13: 40; 2012-05-20: 40; 2012-05-27: 40; 2012-06-03: 40; 2012-06-10: 40; 2012-06-17: 40
Pipeline | TBD Rails | Chronicle | SOW3 - Trajan MVP | Rails | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 40; 2012-04-22: 40; 2012-04-29: 40; 2012-05-06: 40; 2012-05-13: 40; 2012-05-20: 40; 2012-05-27: 40; 2012-06-03: 40; 2012-06-10: 40; 2012-06-17: 40
Pipeline | TBD Rails | Chronicle | SOW3 - Trajan MVP | Rails | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 40; 2012-04-22: 40; 2012-04-29: 40; 2012-05-06: 40; 2012-05-13: 40; 2012-05-20: 40; 2012-05-27: 40; 2012-06-03: 40; 2012-06-10: 40; 2012-06-17: 40
Pipeline | TBD Rails | Chronicle | SOW3 - Trajan MVP | Rails | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 40; 2012-04-22: 40; 2012-04-29: 40; 2012-05-06: 40; 2012-05-13: 40; 2012-05-20: 40; 2012-05-27: 40; 2012-06-03: 40; 2012-06-10: 40; 2012-06-17: 40
Pipeline | Linus Liu | Chronicle | SOW3 - Trajan MVP | QA | FALSE |  | 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 16; 2012-03-18: 16; 2012-03-25: 20; 2012-04-01: 20; 2012-04-08: 20; 2012-04-15: 20; 2012-04-22: 20; 2012-04-29: 20; 2012-05-06: 20; 2012-05-13: 20; 2012-05-20: 20; 2012-05-27: 20; 2012-06-03: 20; 2012-06-10: 20; 2012-06-17: 20
Booked | Anthony Nystrom | Agilysys | AGYS SOW11 - Android IG Retainer | PM | TRUE | 4 | 2012-01-08: 4; 2012-01-15: 4; 2012-01-22: 4
Booked | Chris Tate | Agilysys | AGYS SOW11 - Android IG Retainer | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0
Booked | Curt Hu | Agilysys | AGYS SOW11 - Android IG Retainer | Mobile/Eng | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0
Booked | Daniil Degtyarev | Agilysys | AGYS SOW11 - Android IG Retainer | Mobile/Eng | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0
Booked | Jurgen Altziebler | Agilysys | AGYS SOW11 - Android IG Retainer | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0
Booked | Linus Liu | Agilysys | AGYS SOW11 - Android IG Retainer | QA | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0
Booked | Patti Chan | Agilysys | AGYS SOW11 - Android IG Retainer | PM | TRUE | 4 | 2012-01-08: 4; 2012-01-15: 4; 2012-01-22: 4
Booked | Roger Frost | Agilysys | AGYS SOW11 - Android IG Retainer | Mobile/Eng | TRUE | 40 | 2012-01-08: 40; 2012-01-15: 40; 2012-01-22: 40
Booked | Anthony Nystrom | Agilysys | AGYS SOW12 - Elevate Retainer | PM | TRUE | 0 | 2012-01-08: 0
Booked | Chris Tate | Agilysys | AGYS SOW12 - Elevate Retainer | UX | TRUE | 0 | 2012-01-08: 0
Booked | Daniel Lv | Agilysys | AGYS SOW12 - Elevate Retainer | Rails | TRUE | 32 | 2012-01-08: 0
Booked | Ian Yang | Agilysys | AGYS SOW12 - Elevate Retainer | Rails | TRUE | 0 | 2012-01-08: 0
Booked | Jurgen Altziebler | Agilysys | AGYS SOW12 - Elevate Retainer | PM | TRUE | 0 | 2012-01-08: 0
Booked | Linus Liu | Agilysys | AGYS SOW12 - Elevate Retainer | QA | TRUE | 0 | 2012-01-08: 0
Booked | Patti Chan | Agilysys | AGYS SOW12 - Elevate Retainer | PM | TRUE | 4 | 2012-01-08: 4
Booked | Ping Yu | Agilysys | AGYS SOW12 - Elevate Retainer | Rails | TRUE | 0 | 2012-01-08: 2
Booked | Anthony Nystrom | BlueShift Local | SOW1 - DoTell Mobile App | PM | TRUE | 5 | 2012-01-08: 5; 2012-01-15: 5; 2012-01-22: 3; 2012-01-29: 0
Booked | Ben Markowitz | BlueShift Local | SOW1 - DoTell Mobile App | UX | TRUE | 1 | 2012-01-08: 1; 2012-01-15: 1; 2012-01-22: 0; 2012-01-29: 0
Booked | Insiya Hussain | BlueShift Local | SOW1 - DoTell Mobile App | PM | TRUE | 0 | 2012-01-08: 10; 2012-01-15: 10; 2012-01-22: 6; 2012-01-29: 4
Booked | Jurgen Altziebler | BlueShift Local | SOW1 - DoTell Mobile App | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0
Booked | Linus Liu | BlueShift Local | SOW1 - DoTell Mobile App | QA | TRUE | 10 | 2012-01-08: 10; 2012-01-15: 10; 2012-01-22: 6; 2012-01-29: 0
Booked | Stefano Falasca | BlueShift Local | SOW1 - DoTell Mobile App | Mobile/Eng | TRUE | 42 | 2012-01-08: 42; 2012-01-15: 42; 2012-01-22: 25; 2012-01-29: 8
Booked | Ram Dobson | Intridea | Surfiki | Rails | FALSE |  | 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0
Booked | Anthony Nystrom | Swapt | SOW 1 - Website | PM | TRUE | 0 | 2012-01-08: 0
Booked | Ben Markowitz | Swapt | SOW 1 - Website | UX | TRUE | 0 | 2012-01-08: 0
Booked | Chris Tate | Swapt | SOW 1 - Website | UX | TRUE | 0 | 2012-01-08: 0
Booked | Javier Rios | Swapt | SOW 1 - Website | HTML/JS | TRUE | 0 | 2012-01-08: 0
Booked | Jurgen Altziebler | Swapt | SOW 1 - Website | PM | TRUE | 0 | 2012-01-08: 0
Booked | Linus Liu | Swapt | SOW 1 - Website | QA | TRUE | 0 | 2012-01-08: 0
Booked | Patti Chan | Swapt | SOW 1 - Website | PM | TRUE | 0 | 2012-01-08: 4
Booked | Ram Dobson | Swapt | SOW 1 - Website | Rails | TRUE | 32 | 2012-01-08: 16
Booked | Tran Thanh | Swapt | SOW 1 - Website | HTML/JS | TRUE | 0 | 2012-01-08: 0
Booked | Youcai Qian | Swapt | SOW 1 - Website | Rails | TRUE | 17 | 2012-01-08: 16
Booked | Anthony Nystrom | SYPartners | SOW 1 - Staff Augmentation | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Mike Fischer | SYPartners | SOW 1 - Staff Augmentation | Rails | TRUE | 40 | 2012-01-08: 40; 2012-01-15: 40
Booked | Anthony Nystrom | OraMetrix | SOW1 - SureSmile Web Application | PM | TRUE | 0 | 2012-01-08: 0
Booked | Chris Tate | OraMetrix | SOW1 - SureSmile Web Application | UX | TRUE | 4 | 2012-01-08: 2
Booked | Insiya Hussain | OraMetrix | SOW1 - SureSmile Web Application | PM | TRUE | 0 | bar: 2012-01-08
Booked | Jurgen Altziebler | OraMetrix | SOW1 - SureSmile Web Application | PM | TRUE | 2 | 2012-01-08: 2
Booked | Serign Jobe | OraMetrix | SOW1 - SureSmile Web Application | Rails | TRUE | 2 | 2012-01-08: 2
Booked | Michael Tierney | OraMetrix | SOW1 - SureSmile Web Application | HTML/JS | TRUE | 32 | 2012-01-08: 30
Booked | Ram Dobson | Consumer Source Holdings Inc. | SOW2 - Web Development Retainer | Rails | TRUE |  | 2012-01-08: 24; 2012-01-15: 40; 2012-01-22: 40; 2012-01-29: 40; 2012-02-05: 40; 2012-02-12: 40; 2012-02-19: 40; 2012-02-26: 40; 2012-03-04: 40; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40
Booked | Anthony Nystrom | Mitsubishi | MePresent | PM | TRUE | 8 | 2012-01-08: 8; 2012-01-15: 8
Booked | Ben Markowitz | Mitsubishi | MePresent | UX | TRUE | 4 | 2012-01-08: 0; 2012-01-15: 0
Booked | Curt Hu | Mitsubishi | MePresent | Mobile/Eng | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Jeff Baier | Mitsubishi | MePresent | Mobile/Eng | TRUE | 16 | 2012-01-08: 20; 2012-01-15: 20
Booked | Jurgen Altziebler | Mitsubishi | MePresent | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Linus Liu | Mitsubishi | MePresent | QA | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Maggie Lubberts | Mitsubishi | MePresent | PM | TRUE | 4 | 2012-01-08: 8; 2012-01-15: 8
Booked | Yong Gu | Mitsubishi | MePresent | Mobile/Eng | TRUE | 16 | 2012-01-08: 20; 2012-01-15: 20
Booked | Anthony Nystrom | Mitsubishi | MeQuote Global | PM | TRUE | 8 | 2012-01-08: 8; 2012-01-15: 8
Booked | Ben Markowitz | Mitsubishi | MeQuote Global | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Jeff Baier | Mitsubishi | MeQuote Global | Mobile/Eng | TRUE | 16 | 2012-01-08: 20; 2012-01-15: 20
Booked | Jurgen Altziebler | Mitsubishi | MeQuote Global | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0
Booked | Linus Liu | Mitsubishi | MeQuote Global | QA | TRUE | 8 | 2012-01-08: 16; 2012-01-15: 16
Booked | Maggie Lubberts | Mitsubishi | MeQuote Global | PM | TRUE | 4 | 2012-01-08: 8; 2012-01-15: 8
Booked | Yong Gu | Mitsubishi | MeQuote Global | Mobile/Eng | TRUE | 16 | 2012-01-08: 20; 2012-01-15: 20
| Ram Dobson | Intridea | Internal::Paid Time Off | Rails | FALSE | 8 | 2012-01-22: 8
Booked | Ben Markowitz | Chronicle | SOW2 - User Experience Retainer | UX | TRUE | 12 | 2012-01-08: 18; 2012-01-15: 18; 2012-01-22: 18; 2012-01-29: 14; 2012-02-05: 14; 2012-02-12: 14; 2012-02-19: 20; 2012-02-26: 20; 2012-03-04: 0; 2012-03-11: 4
Booked | Chris Tate | Chronicle | SOW2 - User Experience Retainer | UX | TRUE | 6 | 2012-01-08: 6; 2012-01-15: 4; 2012-01-22: 4; 2012-01-29: 2; 2012-02-05: 2; 2012-02-12: 2; 2012-02-19: 2; 2012-02-26: 2; 2012-03-04: 2; 2012-03-11: 0
Booked | Insiya Hussain | Chronicle | SOW2 - User Experience Retainer | PM | TRUE | 0 | 2012-01-08: 2; 2012-01-15: 2; 2012-01-22: 2; 2012-01-29: 1; 2012-02-05: 1; 2012-02-12: 1; 2012-02-19: 3; 2012-02-26: 3; 2012-03-04: 0; 2012-03-11: 0
Booked | Jurgen Altziebler | Chronicle | SOW2 - User Experience Retainer | PM | TRUE | 2 | 2012-01-08: 2; 2012-01-15: 2; 2012-01-22: 2; 2012-01-29: 1; 2012-02-05: 1; 2012-02-12: 1; 2012-02-19: 1; 2012-02-26: 1; 2012-03-04: 1; 2012-03-11: 0
Booked | Javier Rios | Chronicle | SOW2 - User Experience Retainer | HTML/JS | TRUE | 12 | 2012-01-08: 18; 2012-01-15: 18; 2012-01-22: 18; 2012-01-29: 18; 2012-02-05: 18; 2012-02-12: 18; 2012-02-19: 18; 2012-02-26: 18; 2012-03-04: 40; 2012-03-11: 8
Booked | Michael Tierney | Chronicle | SOW2 - User Experience Retainer | HTML/JS | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 4; 2012-02-26: 4; 2012-03-04: 0; 2012-03-11: 0
Booked | Insiya Hussain | Intridea | Marketing PR | PM | FALSE |  | 2012-01-29: 0
Booked | Insiya Hussain | Intridea | yourtime.intridea.com | PM | FALSE |  | 2012-01-15: 4; 2012-01-22: 4; 2012-01-29: 4; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 2; 2012-02-26: 2; 2012-03-04: 2
Booked | Insiya Hussain | Intridea | intridea.com | (PM) | FALSE |  | 2012-01-15: 8
| Insiya Hussain | Intridea | Internal::Paid Time Off | (PM) | FALSE | 40 | 2012-01-08: 16; 2012-03-04: 24
Booked | Insiya Hussain | OraMetrix | SOW2 - SureSmile Web Application | PM | TRUE |  | 2012-01-15: 2; 2012-01-22: 2; 2012-01-29: 2; 2012-02-05: 1; 2012-02-12: 1; 2012-02-19: 1; 2012-02-26: 1; 2012-03-04: 1; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Pipeline | Insiya Hussain | Vivere | SOW 1 - Healthcare App | PM | FALSE |  | 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0
Booked | Insiya Hussain | Cato Institute | SOW1 - Libertarianism.org responsive design | PM | TRUE |  | 2012-01-15: 4; 2012-01-22: 4; 2012-01-29: 4; 2012-02-05: 4; 2012-02-12: 4; 2012-02-19: 4; 2012-02-26: 4; 2012-03-04: 4; 2012-03-11: 4; 2012-03-18: 4
Booked | Roger Frost | Consumer Source Holdings Inc. | SOW2 - Web Development Retainer | Rails | TRUE |  | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 40; 2012-02-19: 40; 2012-02-26: 40; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Daniil Degtyarev | Consumer Source Holdings Inc. | SOW4 - Web Development Services | Rails | TRUE |  | 2012-02-19: 30; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Anthony Nystrom | OraMetrix | SOW2 - SureSmile Web Application | PM | TRUE |  | 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Chris Tate | OraMetrix | SOW2 - SureSmile Web Application | UX | TRUE |  | 2012-01-15: 4; 2012-01-22: 4; 2012-01-29: 4; 2012-02-05: 2; 2012-02-12: 2; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 1; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Jurgen Altziebler | OraMetrix | SOW2 - SureSmile Web Application | PM | TRUE |  | 2012-01-15: 2; 2012-01-22: 2; 2012-01-29: 2; 2012-02-05: 1; 2012-02-12: 1; 2012-02-19: 1; 2012-02-26: 1; 2012-03-04: 2; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Serign Jobe | OraMetrix | SOW2 - SureSmile Web Application | Rails | TRUE |  | 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Michael Tierney | OraMetrix | SOW2 - SureSmile Web Application | HTML/JS | TRUE |  | 2012-01-15: 40; 2012-01-22: 40; 2012-01-29: 40; 2012-02-05: 36; 2012-02-12: 36; 2012-02-19: 12; 2012-02-26: 18; 2012-03-04: 18; 2012-03-11: 10; 2012-03-18: 10; 2012-03-25: 20
Booked | Andy Wang | Pew Research Center | GRF Development | Rails | TRUE | 24 | 2012-01-08: 40; 2012-01-15: 32; 2012-01-22: 24; 2012-01-29: 40; 2012-02-05: 40; 2012-02-12: 0; 2012-02-19: 40; 2012-02-26: 10
Booked | Anthony Nystrom | Pew Research Center | GRF Development | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0
Booked | Ben Markowitz | Pew Research Center | GRF Development | UX | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0
Booked | Javier Rios | Pew Research Center | GRF Development | HTML/JS | TRUE | 20 | 2012-01-08: 20; 2012-01-15: 20; 2012-01-22: 20; 2012-01-29: 20; 2012-02-05: 10; 2012-02-12: 10; 2012-02-19: 2; 2012-02-26: 0
Booked | Jurgen Altziebler | Pew Research Center | GRF Development | PM | TRUE | 16 | 2012-01-08: 16; 2012-01-15: 16; 2012-01-22: 8; 2012-01-29: 8; 2012-02-05: 8; 2012-02-12: 8; 2012-02-19: 8; 2012-02-26: 4
Booked | Linus Liu | Pew Research Center | GRF Development | QA | TRUE | 8 | 2012-01-08: 8; 2012-01-15: 0; 2012-01-22: 16; 2012-01-29: 16; 2012-02-05: 16; 2012-02-12: 0; 2012-02-19: 8; 2012-02-26: 8
Booked | Maggie Lubberts | Pew Research Center | GRF Development | PM | TRUE | 8 | 2012-01-08: 16; 2012-01-15: 16; 2012-01-22: 16; 2012-01-29: 16; 2012-02-05: 16; 2012-02-12: 16; 2012-02-19: 16; 2012-02-26: 8
Booked | Peter Gumeson | Pew Research Center | GRF Development | Rails | TRUE | 16 | 2012-01-08: 20; 2012-01-15: 20; 2012-01-22: 8; 2012-01-29: 4; 2012-02-05: 4; 2012-02-12: 4; 2012-02-19: 0; 2012-02-26: 0
Booked | Roc Yu | Pew Research Center | GRF Development | Rails | TRUE | 32 | 2012-01-08: 40; 2012-01-15: 40; 2012-01-22: 40; 2012-01-29: 40; 2012-02-05: 40; 2012-02-12: 0; 2012-02-19: 40; 2012-02-26: 20
Booked | Tran Thanh | Pew Research Center | GRF Development | HTML/JS | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0
Booked | Ben Markowitz | Scalr | Visual Design | UX | FALSE | 0 | 2012-01-08: 10; 2012-01-15: 10; 2012-01-22: 10; 2012-01-29: 4
Booked | Jurgen Altziebler | Scalr | Visual Design | PM | FALSE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0
Booked | John Reigart | Intridea | intridea.com | (PM) | FALSE |  | 2012-04-22: 0
Booked | Anthony Nystrom | Opower | SOW1 - Rewards App | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Ian Yang | Opower | SOW1 - Rewards App | Rails | TRUE | 32 | 2012-01-08: 20; 2012-01-15: 8; 2012-01-22: 8; 2012-01-29: 8; 2012-02-05: 16; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 20; 2012-03-11: 0; 2012-03-18: 16; 2012-03-25: 0
Booked | Jurgen Altziebler | Opower | SOW1 - Rewards App | PM | TRUE | 0 | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Linus Liu | Opower | SOW1 - Rewards App | QA | TRUE | 2 | 2012-01-08: 2; 2012-01-15: 2; 2012-01-22: 2; 2012-01-29: 2; 2012-02-05: 2; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 2; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0
Booked | Patti Chan | Opower | SOW1 - Rewards App | PM | TRUE | 8 | 2012-01-08: 4; 2012-01-15: 2; 2012-01-22: 4; 2012-01-29: 4; 2012-02-05: 4; 2012-02-12: 2; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 4; 2012-03-11: 4; 2012-03-18: 4; 2012-03-25: 0
Booked | Peter Gumeson | Opower | SOW1 - Rewards App | Rails | TRUE | 16 | 2012-01-08: 16; 2012-01-15: 12; 2012-01-22: 8; 2012-01-29: 16; 2012-02-05: 16; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 20; 2012-03-04: 16; 2012-03-11: 6; 2012-03-18: 4; 2012-03-25: 0
Booked | Anthony Nystrom | Opower | SOW2 - Tipsy App MVP | PM | TRUE |  | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0
Booked | Patti Chan | Opower | SOW2 - Tipsy App MVP | PM | TRUE |  | 2012-01-08: 6; 2012-01-15: 6; 2012-01-22: 6; 2012-01-29: 6; 2012-02-05: 6; 2012-02-12: 6; 2012-02-19: 4; 2012-02-26: 4; 2012-03-04: 2
Booked | Ian Yang | Opower | SOW2 - Tipsy App MVP | Rails | TRUE |  | 2012-01-08: 0; 2012-01-15: 32; 2012-01-22: 32; 2012-01-29: 32; 2012-02-05: 24; 2012-02-12: 16; 2012-02-19: 40; 2012-02-26: 20; 2012-03-04: 8
Booked | Peter Gumeson | Opower | SOW2 - Tipsy App MVP | Rails | TRUE |  | 2012-01-08: 0; 2012-01-15: 8; 2012-01-22: 24; 2012-01-29: 20; 2012-02-05: 20; 2012-02-12: 20; 2012-02-19: 40; 2012-02-26: 20; 2012-03-04: 2
Booked | Linus Liu | Opower | SOW2 - Tipsy App MVP | QA | TRUE |  | 2012-01-08: 0; 2012-01-15: 0; 2012-01-22: 0; 2012-01-29: 4; 2012-02-05: 4; 2012-02-12: 4; 2012-02-19: 4; 2012-02-26: 2; 2012-03-04: 0
Booked | Anthony Nystrom | Swapt | SOW 1 - Website | PM | FALSE |  | 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0
Booked | Patti Chan | Swapt | SOW 1 - Website | PM | FALSE |  | 2012-02-26: 4; 2012-03-04: 4; 2012-03-11: 4; 2012-03-18: 4; 2012-03-25: 4; 2012-04-01: 1
Booked | Tom Zeng | Swapt | SOW 1 - Website | Rails | FALSE |  | 2012-02-26: 8; 2012-03-04: 8; 2012-03-11: 8; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0
Booked | Youcai Qian | Swapt | SOW 1 - Website | Rails | FALSE |  | 2012-02-26: 16; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0
Booked | Yong Gu | Swapt | SOW 1 - Website | Rails | FALSE |  | 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 16; 2012-03-18: 16; 2012-03-25: 16; 2012-04-01: 4
Booked | Jurgen Altziebler | WeWork | SOW 1 - UX for Back Office Asset Management | PM | FALSE |  | 2012-01-29: 0; 2012-02-05: 0; 2012-02-12: 0; 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0
Booked | Patti Chan | WeWork | SOW 1 - UX for Back Office Asset Management | PM | FALSE |  | 2012-01-29: 10; 2012-02-05: 8; 2012-02-12: 4; 2012-02-19: 8; 2012-02-26: 8; 2012-03-04: 12; 2012-03-11: 0; 2012-03-18: 4; 2012-03-25: 0; 2012-04-01: 1
Booked | Maggie Lubberts | WeWork | SOW 1 - UX for Back Office Asset Management | PM | FALSE |  | 2012-01-29: 6; 2012-02-05: 4; 2012-02-12: 4; 2012-02-19: 2; 2012-02-26: 2; 2012-03-04: 2; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0
Booked | Chris Tate | WeWork | SOW 1 - UX for Back Office Asset Management | UX | FALSE |  | 2012-01-29: 20; 2012-02-05: 32; 2012-02-12: 32; 2012-02-19: 24; 2012-02-26: 16; 2012-03-04: 20; 2012-03-11: 0; 2012-03-18: 4; 2012-03-25: 0; 2012-04-01: 7
| Javier Rios | Intridea | Internal::Paid Time Off | HTML/JS | FALSE | 8
Booked | Jeff Baier | Cato Institute | SOW2 - Human Progress | Rails | TRUE |  | 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 4; 2012-04-01: 4; 2012-04-08: 4; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 0; 2012-05-20: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Anthony Nystrom | Consumer Source Holdings Inc. | SOW4 - Web Development Services | PM | TRUE |  | 2012-02-19: 0; 2012-02-26: 0; 2012-03-04: 0; 2012-03-11: 0; 2012-03-18: 0; 2012-03-25: 0; 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0
Booked | Youcai Qian | Consumer Source Holdings Inc. | SOW4 - Web Development Services | Rails | TRUE |  | 2012-02-19: 0; 2012-02-26: 16; 2012-03-04: 30; 2012-03-11: 30; 2012-03-18: 30; 2012-03-25: 30; 2012-04-01: 30; 2012-04-08: 30; 2012-04-15: 30; 2012-04-22: 30
Booked | Tom Zeng | Consumer Source Holdings Inc. | SOW4 - Web Development Services | Rails | TRUE |  | 2012-02-19: 10; 2012-02-26: 10; 2012-03-04: 10; 2012-03-11: 20; 2012-03-18: 20; 2012-03-25: 20; 2012-04-01: 20; 2012-04-08: 20; 2012-04-15: 10; 2012-04-22: 10
Booked | Mike Fischer | Consumer Source Holdings Inc. | SOW4 - Web Development Services | Rails | TRUE |  | 2012-02-19: 40; 2012-02-26: 40; 2012-03-04: 40; 2012-03-11: 40; 2012-03-18: 40; 2012-03-25: 40; 2012-04-01: 40; 2012-04-08: 40; 2012-04-15: 24; 2012-04-22: 0
Booked | TBD HTML/JS | American Bible Society | SOW1 - Scripture Analytics Dashboard | HTML/JS | TRUE |  | 2012-04-01: 0; 2012-04-08: 0; 2012-04-15: 0; 2012-04-22: 0; 2012-04-29: 0; 2012-05-06: 0; 2012-05-13: 20; 2012-05-20: 20; 2012-05-27: 20; 2012-06-03: 16; 2012-06-10: 16; 2012-06-17: 8; 2012-06-24: 0; 2012-07-01: 0
Booked | Javier Rios | Intridea | intridea.com | HTML/JS | FALSE |  | 2012-03-18: 0; 2012-04-22: 0
Booked | Linus Liu | Intridea | intridea.com | QA | FALSE |  | 2012-03-18: 0; 2012-04-22: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Serign Jobe | Intridea | intridea.com | Rails | FALSE |  | 2012-01-22: 8; 2012-01-29: 8; 2012-03-18: 0; 2012-04-22: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Tom Zeng | Intridea | intridea.com | Rails | FALSE |  | 2012-01-15: 40; 2012-01-22: 40; 2012-01-29: 40; 2012-03-18: 0; 2012-04-22: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Peter Gumeson | Intridea | intridea.com | Rails | FALSE |  | 2012-03-18: 0; 2012-04-22: 0; 2012-05-27: 0; 2012-06-03: 0; 2012-06-10: 0; 2012-06-17: 0; 2012-06-24: 0
Booked | Javier Rios | Department of Energy | SOW1 - Rails Training | HTML/JS | TRUE |  | 2012-01-08: 8
Booked | Jurgen Altziebler | Department of Energy | SOW1 - Rails Training | PM | TRUE |  | 2012-01-08: 0

## _P_ BENCH Eng
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## _P_ BENCH UX
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## _P_ BENCH PM
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## Overbooked
|  | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of 1/6/2013 | SUM of 1/13/2013 | SUM of 1/20/2013 | SUM of 1/27/2013
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41280 | 41287 | 41294
Rails | Yong Gu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## _P_ BENCH Detail
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## Pipeline
[10 empty] | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:
[7 empty] | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## _P_ PTO
| SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of | SUM of 1/6/2013
Grand Total

## _P_ Projects
#VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator: | #VALUE!:blankIndicator:

## Revenue
| SUM of | SUM of | SUM of | SUM of | Rate | Revenue | Adj. Revenue
Grand Total |  |  |  |  | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0
[5 empty] | 165 | 0 | 0
[5 empty] | 165 | 0 | 0
[5 empty] | 165 | 0 | 0
[5 empty] | 165 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 175 | 0 | 0
[5 empty] | 30 | 0 | 0
[5 empty] | 162.5 | 0 | 0
[5 empty] | 75 | 0 | 0
[5 empty] | 135 | 0 | 0
[5 empty] | n/a | 0 | 0
[5 empty] | n/a | 0 | 0 | #DIV/0!:divZero

## Resources
Harvest Name | Name | Status | TZ Offset (standard)
Adam Bair | Adam Bair | FTE | -5
Amelia Saletan | Amelia Saletan | FTE | -5
Anthony Nystrom | Anthony Nystrom | FTE | -6
Andy Wang | Andy Wang | 1099 | 7
Ana Barcelona | Ana Barcelona | 1099 | -5
Ben He | Ben He | 1099 | 7
Ben Markowitz | Ben Markowitz | 1099 | 7
Brian Glusman | Brian Glusman | FTE | -5
Chris Tate | Christopher Tate | 1099 | -5
Chris Selmer | Chris Selmer | FTE | -5
Curt Hu | Daniel Lv | 1099 | 7
Daniel Lv | Daniel Lv | 1099 | 7
Daniil Degtyarev | Daniil Degtyarev | 1099 | 4
Dingding Ye | Dingding Ye | 1099 | 7
Dinny Wu | Dinny (Haifeng) Wu | 1099 | 7
Ted O'Meara | Edward (Ted) O'Meara | FTE | -5
Roc Yu | Feipeng (Roc) Yu | 1099 | 7
Ian Yang | Ian Yang | 1099 | 7
Jake Mauer | Jake (Jacob) Mauer | 1099 | -6
Jan Xie | Jan Xie | 1099 | 7
Javier Rios | Javier Rios | FTE | 7
Jerry Cheung | Jerry (Lik) Cheung | FTE | -8
John Reigart | John Reigart | FTE
Jonathan Marbutt | Jonathan Marbutt | 1099 | -5
Jurgen Altziebler | Jurgen Altziebler | FTE | -5
Justin Seidl | Justin Seidl | 1099 | -5
Kai Chen | Kai Chen | 1099 | 7
Kathleen Selmer | Kathleen Selmer | FTE | -7
Maggie Lubberts | Maggie Lubberts | FTE
Marc Garrett | Marc Garrett | FTE | -5
Michael Bleigh | Michael Bleigh | FTE | -6
Neal Gehrig | Neal Gehrig | FTE | -8
Patti Chan | Patricia Chan | FTE | -8
Paul Ostazeski | Paul Ostazeski | FTE | -5
Peter Jackson | Peter Jackson | FTE | -5
Peter Gumeson | Peter Gumeson | FTE | -8
Ping Yu | Ping Yu | FTE | -6
Raecoo Cao | Raecoo Cao | 1099 | 7
Roger Frost | Roger Frost | 1099
Renae Bair | Renae Bair | 1099 | -5
Sam Yang | Sam Yang | 1099 | 7
Stefano Falasca | Stefano Falasca | 1099 | 4
Terry Tai | Terry Tai | 1099 | 7
Thaddeus Selden | Thaddeus (Thadd) Selden | FTE | -5
TBD | TBD | FTE
Linus Liu | Xianfeng (Linus) Liu | 1099 | 7
Yong Zhi | Xueyong Zhi | FTE | -5
Yincan Sheng | Yincan Sheng | 1099 | 7
Yong Gu | Yong Gu | 1099 | 7
Youcai Qian | Youcai Qian | 1099 | 7